## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
UI | High | User | find the functions easily | not read a manual to use the app
UI | High | User | Select one of many options from a main menu | access different features easily
UI | High | User | Easy navigate between pages | access different features easily
UI | High | Transaction creater | Be shown a confirmation page upon creating a transaction | create a transaction
UI | Medium | Developer | Create an easy-to-use user interface | allow users to enjoy using the app
UI | Low | User | View my transactions in a graph or chart | more easily picture my payables and receivables
UI | Low | User | have transation split with a slider | visually see the amount of split
UI | Low | User | Change the color theme of the app | have more veriety
UI | Low | User | visably see each transaction in my history as green/red colored | be visably pleased in my history page
UI | Low | Developer | play a sound on receiving a new notification | alert the user of updates
Features | High | User | Add a new contact via email address | add contacts to contact list
Features | High | User | Delete existing contact | delete existing contact
Features | High | User | Request a transaction to be closed as "Paid" | so my lender knows I paid it
Features | High | User | Close a transaction | close a transaction
Features | Medium | User | Easily add friends to a transaction | Quickly fill out a transaction form.
Features | Medium | User | I want to modify a transaction | fix a mistake
Features | Medium | User | Confirm that my due amount is the right amount | make sure the person creating transaction doesn't con me
Features | Medium | User | save my email login info | easliy log in by typing in password only
Features | Medium | User | Search transactions by Group | view all transactions to or from members of a given group
Features | Medium | User | Create contact groups | quickly select contacts from my own shortcut lists
Features | Medium | User | Add contact(s) to transaction from Group list | avoid scrolling through entire contact list to pick preferred contacts
Features | Medium | User/Developer | Report an error | Have a better functioning app
Features | Low | User | Split transaction in an uneven way | allow for potential real-life adjustments
Features | Low | User | I want to add a deadline | get money
Features | Low | user | have a financial tracker/money book | keep track of personal finances
Features | Low | User | Send messages to my contact | so I can be more connected with my contacts
Features | Low | User | access my transaction history on an alternate device | keep track of personal finances anywhere and everywhere
Features | Low | User | Use different currency | use currency other than US dollars
Features | Low | User | Pay in payments | pay over time
Features | Low | User | calculate tips | tip my waitress
Features | Low | User | Login using a facebook account | access the application
Backend | High | Developer | ask security questions of the user | verify that the user is who they say they are
Backend | High | Developer | Access the database | easily edit server data
Backend | High | Developer | Create a database of all transactions | allow users to keep track of who owes who how much
Backend | High | Transaction creater | Adjust the debt per person selected in a transaction | create a transaction
Backend | High | Transaction creater | Enter an amount of the transaction in USD | create a transaction
Backend | High | Transaction creater | Enter comments to associate with a transaction | create a transaction
Backend | High | Transaction creater | Select borrowers from a list of contacts | create a transaction
Backend | High | User | Create an account | use the application
Backend | High | User | Log out | Secure the data so no one else can access it with out my permission
Backend | High | User | quickly access my past transactions | check my transaction history
Backend | High | User | Change my password | change my password to avoid an account compromise
Backend | High | User | Login to an existing account | access the application
Backend | Medium | User | Receive notifications when a transaction has been made | Stay notified of new transactions made by friends.
Backend | Medium | User | edit my email address | change my email without creating a new account.
Backend | Medium | User | Have my transation/account saved in a cloud | log in anywhere and still be connect to the app
Backend | Medium | User | request my password | get my password in case I forget it
Backend | Low | Developer | Provide a reminder system for debt due | push notifications to users about money owed
Backend | Low | User | Import contacts from phone contacts list | quickly add friends to PayBack contacts list
Backend | Low | User | Import contacts from Google contacts list | quickly add friends to PayBack contacts list
Backend | Low | User | Import contacts from Facebook friends list | quickly add friends to PayBack contacts list
Backend | Low | User | Change my name | Change my name
Note on V1: User stories provide a high-level overview of product requirements.

## Product Backlog
Product Backlog
Theme | Item | Hrs | Priority
UI | Create project files/folders and upload to github | 2 | High | Completed
UI | Create a login splash screen | 4 | High | Completed
UI | Create login credentials input boxes on splash screen | 4 | High | Completed
UI | Create Main Menu page w/ buttons for navigating to other pages | 4 | High | Completed
UI | Create menu option for creating a transaction and link to transaction creation page | 1 | Medium | Completed
UI | Create menu option for resolving a transaction and link to transaction resolution page | 1 | Medium | Completed
UI | Create menu option for accessing the contact list and link to contact list page | 1 | Medium | Completed
UI | Create menu option for managing groups and link to group management page | 1 | Medium | Completed
UI | Create menu option for accessing payment statistics and history and link to history page | 1 | Low | Completed
UI | Create menu option for accessing system settings and link to setting page | 1 | Low | Completed
UI | Create menu option for accessing notifications and link to notifications page | 1 | Low | Completed
UI | Create transaction creation page 1 (information collection page) | 4 | High | Completed
UI | Create transaction creation page 2 (contact selection page) | 4 | High | Completed
UI | Create transaction creation page 3 (lenders share page) | 4 | High | Completed
UI | Create transaction creation page 4 (division of payments page) | 4 | High | Completed
UI | Create transaction creation page 5 (summary page) | 4 | High | Completed
UI | Create transaction resolution page | 4 | High
UI | Create contact list page | 4 | High
UI | Create "add contact" page sequence | 4 | High
UI | Create group management page | 2 | High
UI | Create payment statistics page | 8 | High
UI | Create system setting page | 2 | High
UI | Create notifications page | 2 | High
UI | Display number of notifications on main menu page | 4 | Medium
UI | Populate settings page with account and system options | 4 | High
UI | Create a graphical representation of payment statistics | 8 | Low
UI | Implement a logout button option from main menu | 2 | Low
UI | Create a sound alert upon receiving a notification | 2 | Low
UI | Minor aesthetic improvements | 4 | Low
Features | Create method of adding a new contact via email address | 2 | Medium
Features | Capture Adding friend by email address | 2 | Medium
Features | Add option to delete existing contacts within the contact list page | 2 | Low
Features | Add option to "create new group" within group management page | 2 | Medium
Features | Create display of user's created groups in group management page | 4 | Medium
Features | Add option to change existing group information within group management page | 2 | Low
Features | Provide the ability for a user to save log in information | 4 | Low
Features | Integrate the Facebook API to allow facebook log in into the application | 4 | Low
Features | Allow transaction cost to be split unevenly among contacts when creating a transaction | 2 | Medium
Features | Display group labels and individual contacts on the contact select (creating transactions) | 2 | High
Features | Allow the option of a lender to resolve their created transaction on the resolve page | 4 | Medium
Features | Allow the option of a lender to modify their created transaction on the summary page | 1 | Medium
Features | Set up notifications for contacts of transactions they did not create to confirm them | 8 | Low
Features | Allow the user of the app to send an error report to the developers. | 4 | Low
Features | Allow the borrower to pay off their debt using payments | 4 | Low
Features | Provide a tip calculator sub function in the application | 4 | Medium
Features | Provide the option of imputing the transaction cost in different currencies | 4 | Low
Features | Allow the user to send messages to their contacts through their contact list page | 4 | Medium
Features | Allow the user to track their payment history and income/outgoing money in summary | 4 | High
Features | Allow the transaction creator to place a deadline on repayment of the transaction | 4 | Low
Features | Allow the user to access their transaction history from alternate devices | 8 | Medium
Features | Handle Login information | 8 | High
Features | Provide method for authentication of logins/accounts | 4 | High
Features | Create transaction page 1 (Information gather) | 2 | High
Features | Create transaction page 2 + 4 (Contact selection / borrower's share) | 16 | High
Features | Create transaction page 3 ( Lender's share) debt division selection | 4 | High
Features | Create transaction page 5 ( Summary) | 4 | High
Features | Provide method for pushing transaction object to database. | 2 | High
Features | Have contact selection populated by contact list data | 4 | High
Backend | Create query command for transactions | 2 | High
Backend | Create query command for retreiving contacts | 2 | High
Backend | Create security questions to ask users | 4 | Medium
Backend | Research possible options of where to host database | 4 | High | Completed
Backend | Set up database on server | 8 | High | Completed
Backend | Create table in database for accounts | 4 | High | Completed
Backend | Create table in database for admin | 4 | High
Backend | Create relation in database for transactions | 4 | High | Completed
Backend | Create relation in database for groups | 4 | High
Backend | Create realtion in database for friendOf | 4 | High | Completed
Backend | Create relation in database for notifications | 4 | Medium | Completed
Backend | Write code to query tables | 4 | High
Backend | Write code to update tables | 4 | High | Completed
Backend | Create authentication system for user account validation | 8 | High
Backend | Allow importing contacts from google contact list | 8 | Low
Backend | Allow importing contacts from Facebook contact list | 8 | Low
Backend | Create the option for users to change their name | 4 | Low
Backend | Create the option for users to change their email | 4 | Low
Backend | Enable database encrpytion | 4 | Low
Backend | Research Communication between Android and DB | 4 | High
Backend | Transfer DB to a committed Desktop | 1 | High
Backend | Install Apache and PHP on Desktop | 2 | High
Backend | Establish Server Communication Schema | 1 | Medium
Backend | PHP server code for account creation | 4 | High
Backend | Java Plugin code for server communication | 4 | High
Documentation | Ramp up on Android SDK development | 16 | High | Completed
Documentation | Create GitHub Repository | 1 | High | Completed
Documentation | Sprint 1 reporting presentation | 2 | High | Completed
Documentation | Sprint 2 reporting presentation | 2 | High
Documentation | Sprint 3 reporting presentation | 2 | High
Documentation | Sprint 4 reporting presentation | 2 | High
339
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Sprint 1
Sprint 1 Backlog | [5 empty] | Date | 9/18 - 9/24 |  |  | 9/25 - 10/1 |  |  | 10/2 - 10/8
Backlog Item | Hrs. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Create project files/folders and upload to github | 2 | High | Viquoc | Completed |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a login splash screen | 4 | High | Viquoc | Completed |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create login credentials input boxes on splash screen | 4 | High | Viquoc | Completed |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Main Menu page w/ buttons for navigating to other pages | 4 | High | Arnav, Will | Completed |  |  | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
Create transaction creation page 1 (information collection page) | 4 | High | Tim | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
Create transaction creation page 2 (contact selection page) | 4 | High | Tim | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
Create transaction creation page 3 (lenders share page) | 4 | High | Tim | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
Create transaction creation page 4 (division of payments page) | 4 | High | Tim | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
Create transaction creation page 5 (Summary page) | 4 | Medium | Tim | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0
Create menu option for creating a transaction and link to transaction creation page | 1 | Medium | Arnav, Will | Completed |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Create menu option for resolving a transaction and link to transaction resolution page | 1 | Medium | Tim | Completed |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Create menu option for accessing the contact list and link to contact list page | 1 | Medium | Tim | Completed |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Create menu option for managing groups and link to group management page | 1 | Medium | Tim | Completed |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Create menu option for accessing payment statistics and history and link to history page | 1 | Low | Tim | Completed |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Create menu option for accessing notifications and link to notifications page | 1 | Low | Tim | Completed |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create method of adding a new contact via email address | 4 | Medium | Viquoc | Forwarded |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Research possible options of where to host database | 4 | High | Chase | Completed |  |  | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0
Set up database on server | 8 | High | Ryan, Hohyun | Completed |  |  | 8 | 8 | 8 | 4 | 2 | 2 | 0 | 0 | 0
Create table in database for accounts | 4 | Medium | Ryan, Hohyun | Completed |  |  | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create relation in database for transactions | 4 | Medium | Ryan, Hohyun | Completed |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
Create relation in database for groups | 2 | High | Ryan, Hohyun | Completed |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Create realtion in database for friendOf | 2 | High | Ryan, Hohyun | Completed |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Write code template to query tables | 4 | Low | Ryan, Hohyun | Forwarded |  |  | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2
Write code to update tables | 4 | Low | Ryan, Hohyun | Completed |  |  | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
Ramp up on Android SDK development | 16 | High | All | Completed |  |  | 16 | 8 | 8 | 4 | 4 | 4 | 4 | 0 | 0
Sprint 1 reporting presentation | 2 | High | Tim | Completed |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Create GitHub Repository | 1 | High | Tim | Completed |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total Hrs: |  | 95
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
DATE: | W | F | M | W | F | M | W | F | M
| 2013-09-18 | 2013-09-20 | 2013-09-23 | 2013-09-25 | 2013-09-27 | 2013-09-30 | 2013-10-02 | 2013-10-04 | 2013-10-07
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 95 | 82 | 71 | 59 | 43 | 28 | 16 | 12 | 6
Ideal | 95 | 83.125 | 71.25 | 59.375 | 47.5 | 35.625 | 23.75 | 11.875 | 0

## Sprint 2
Sprint 2 Backlog | [5 empty] | Date | 10/9 - 10/14 |  |  | 10/16 - 10/21 |  |  | 10/23 - 10/28
Backlog Item | Hrs. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Create system setting page | 2 | High | Orr | In Progress |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 6
Create contact list page | 8 | High | Tim | In Progress |  |  | 8 | 8 | 4 | 4 | 2 | 2 | 2 | 2 | 2
Create "add contact" page sequence | 4 | High | Tim | Completed |  |  | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0
Populate settings page with account and system options | 4 | High | Orr | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2
Create menu option for accessing system settings and link to setting page | 1 | Low | Tim | Completed |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement a logout button option from main menu | 2 | Low | Tim | Completed |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Minor aesthetic improvements | 4 | Low | Tim | In Progress |  |  | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2
Create transaction page 1 (Information gather) | 2 | High | Will,Arnav,Huy | In Progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 19
Create transaction page 2 + 4 (Contact selection / borrower's share) | 16 | High | Will,Arnav,Huy | In Progress |  |  | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 2
Create transaction page 3 ( Lender's share) debt division selection | 4 | High | Will,Arnav,Huy | In Progress |  |  | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 1
Create transaction page 5 ( Summary) | 4 | High | Will,Arnav,Huy | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Edit code for android 2.3.3 | 8 | High | Tim | Completed |  |  | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
Handle Login information | 8 | High | Viquoc | In Progress |  |  | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6
Have contact selection populated by contact list data | 4 | High | Will,Arnav,Huy | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Allow transaction cost to be split unevenly among contacts when creating a transaction | 2 | Medium | Will,Arnav,Huy | In Progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Allow the option of a lender to modify their created transaction on the summary page | 1 | Medium | Will,Arnav,Huy | In Progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
Create method of adding a new contact via email address | 2 | Medium | Tim | Completed |  |  | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0
Capture Adding friend by email address | 2 | Medium | Will | In Progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Add option to delete existing contacts within the contact list page | 1 | Low | Tim | In Progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Research Communication between Android and DB | 4 | high | Hohyun | Completed |  |  | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Transfer DB to a committed Desktop | 1 | high | Chase | Completed |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Install Apache and PHP on Desktop | 2 | high | Chase | Completed |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Establish Server Communication Schema | 1 | medium | Ryan, Hohyun, Chase | Completed |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
PHP server code for account creation | 4 | high | Hohyun | Completed |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0
Java Plugin code for server communication | 4 | high | Ryan, Hohyun, Chase | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 6 | GUI
Create authentication system for user account validation | 8 | High | Ryan, Hohyun | In Progress |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 4 | 2 | 19 | Android
Create query command for transactions | 2 | High | Ryan, Hohyun | Completed |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | Backend
Create query command for retreiving contacts | 2 | High | Ryan, Hohyun | Completed |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Report
Create relation in database for notifications | 2 | Medium | Ryan, Hohyun | Completed |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115
Write code to query tables | 4 | Low | Ryan, Hohyun | Completed |  |  | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0
Sprint 2 reporting presentation | 2 | High | Hohyun, Viquoc, Arnav | Completed |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[5 empty] | Total Hrs: |  | 115
[5 empty] | GUI |  | 25 | 23 | 18 | 15 | 11 | 8 | 8 | 6 | 6
[5 empty] | Android |  | 54 | 53 | 53 | 43 | 37 | 33 | 32 | 32 | 19
[5 empty] | Backend |  | 34 | 32 | 26 | 26 | 22 | 22 | 15 | 7 | 3
[5 empty] | Report |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[7 empty] | 2013-10-09 | 2013-10-11 | 2013-10-14 | 2013-10-16 | 2013-10-18 | 2013-10-21 | 2013-10-23 | 2013-10-25 | 2013-10-28
|  |  | names in order of appearance |  | Orr |  | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 2
[5 empty] | Tim |  | 30 | 28 | 23 | 19 | 13 | 6 | 5 | 5 | 5
[5 empty] | Will |  | 13 | 13 | 13 | 10.3333 | 9.6667 | 9.6667 | 9.6667 | 9.6667 | 5.3333
[5 empty] | Arnav |  | 11.6667 | 11.6667 | 11.6667 | 9 | 8.3333 | 8.3333 | 8.3333 | 7.6667 | 3.3333
[5 empty] | Huy |  | 11 | 11 | 11 | 8.3333 | 7.6667 | 7.6667 | 7.6667 | 7.6667 | 3.3333
[5 empty] | Viquoc |  | 8.6667 | 7.6667 | 7.6667 | 6.6667 | 6.6667 | 6.6667 | 6.6667 | 6 | 6
[5 empty] | Hohyun |  | 20.1667 | 18.3333 | 14.3333 | 14.3333 | 11.3333 | 11.3333 | 8.5 | 4.3333 | 1.3333
[5 empty] | Chase |  | 5.5 | 4.6667 | 4.6667 | 4.6667 | 4.6667 | 4.6667 | 1.3333 | 0.33333 | 0.33333
[5 empty] | Ryan |  | 11.5 | 9.6667 | 7.6667 | 7.6667 | 6.6667 | 6.6667 | 5.8333 | 2.3333 | 1.3333
[5 empty] | will,arnav,huy |  | 11 | 11 | 11 | 8.3333 | 7.6667 | 7.6667 | 7.6667 | 7.6667 | 3.3333
[5 empty] | ryan,hohyun |  | 9 | 8 | 6 | 6 | 5 | 5 | 4.5 | 2 | 1
[5 empty] | ryan,hohyun,chase |  | 2.5 | 1.6667 | 1.6667 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 0.33333 | 0.33333
[5 empty] | hohyun,viquoc,arnav |  | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0 | 0
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 2 Burndown
Sprint 2 Burndown Chart
DATE: | W | F | M | W | F | M | W | F | M
| 2013-10-09 | 2013-10-11 | 2013-10-14 | 2013-10-16 | 2013-10-18 | 2013-10-21 | 2013-10-23 | 2013-10-25 | 2013-10-28
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 115 | 110 | 99 | 86 | 72 | 65 | 57 | 45 | 28
Ideal | 115 | 100.625 | 86.25 | 71.875 | 57.5 | 43.125 | 28.75 | 14.375 | 0