## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
UI | High | User | find the functions easily | not read a manual to use the app
UI | High | User | Select one of many options from a main menu | access different features easily
UI | High | User | Easy navigate between pages | access different features easily
UI | High | Transaction creater | Be shown a confirmation page upon creating a transaction | create a transaction
UI | Medium | Developer | Create an easy-to-use user interface | allow users to enjoy using the app
UI | Low | User | View my transactions in a graph or chart | more easily picture my payables and receivables
UI | Low | User | have transation split with a slider | visually see the amount of split
UI | Low | User | Change the color theme of the app | have more veriety
UI | Low | User | visably see each transaction in my history as green/red colored | be visably pleased in my history page
UI | Low | Developer | play a sound on receiving a new notification | alert the user of updates
Features | High | User | Add a new contact via email address | add contacts to contact list
Features | High | User | Delete existing contact | delete existing contact
Features | High | User | Request a transaction to be closed as "Paid" | so my lender knows I paid it
Features | High | User | Close a transaction | close a transaction
Features | Medium | User | Easily add friends to a transaction | Quickly fill out a transaction form.
Features | Medium | User | I want to modify a transaction | fix a mistake
Features | Medium | User | Confirm that my due amount is the right amount | make sure the person creating transaction doesn't con me
Features | Medium | User | save my email login info | easliy log in by typing in password only
Features | Medium | User | Search transactions by Group | view all transactions to or from members of a given group
Features | Medium | User | Create contact groups | quickly select contacts from my own shortcut lists
Features | Medium | User | Add contact(s) to transaction from Group list | avoid scrolling through entire contact list to pick preferred contacts
Features | Medium | User/Developer | Report an error | Have a better functioning app
Features | Low | User | Split transaction in an uneven way | allow for potential real-life adjustments
Features | Low | User | I want to add a deadline | get money
Features | Low | user | have a financial tracker/money book | keep track of personal finances
Features | Low | User | Send messages to my contact | so I can be more connected with my contacts
Features | Low | User | access my transaction history on an alternate device | keep track of personal finances anywhere and everywhere
Features | Low | User | Use different currency | use currency other than US dollars
Features | Low | User | Pay in payments | pay over time
Features | Low | User | calculate tips | tip my waitress
Features | Low | User | Login using a facebook account | access the application
Backend | High | Developer | ask security questions of the user | verify that the user is who they say they are
Backend | High | Developer | Access the database | easily edit server data
Backend | High | Developer | Create a database of all transactions | allow users to keep track of who owes who how much
Backend | High | Transaction creater | Adjust the debt per person selected in a transaction | create a transaction
Backend | High | Transaction creater | Enter an amount of the transaction in USD | create a transaction
Backend | High | Transaction creater | Enter comments to associate with a transaction | create a transaction
Backend | High | Transaction creater | Select borrowers from a list of contacts | create a transaction
Backend | High | User | Create an account | use the application
Backend | High | User | Log out | Secure the data so no one else can access it with out my permission
Backend | High | User | quickly access my past transactions | check my transaction history
Backend | High | User | Change my password | change my password to avoid an account compromise
Backend | High | User | Login to an existing account | access the application
Backend | Medium | User | Receive notifications when a transaction has been made | Stay notified of new transactions made by friends.
Backend | Medium | User | edit my email address | change my email without creating a new account.
Backend | Medium | User | Have my transation/account saved in a cloud | log in anywhere and still be connect to the app
Backend | Medium | User | request my password | get my password in case I forget it
Backend | Low | Developer | Provide a reminder system for debt due | push notifications to users about money owed
Backend | Low | User | Import contacts from phone contacts list | quickly add friends to PayBack contacts list
Backend | Low | User | Import contacts from Google contacts list | quickly add friends to PayBack contacts list
Backend | Low | User | Import contacts from Facebook friends list | quickly add friends to PayBack contacts list
Backend | Low | User | Change my name | Change my name
Note on V1: User stories provide a high-level overview of product requirements.

## Product Backlog
Product Backlog
Theme | Item | Hrs | Priority
UI | Create a login splash screen | 4 | High
UI | Create login credentials input boxes on splash screen | 4 | High
UI | Create Main Menu page w/ buttons for navigating to other pages | 4 | High
UI | Create menu option for creating a transaction and link to transaction creation page | 1 | Medium
UI | Create menu option for resolving a transaction and link to transaction resolution page | 1 | Medium
UI | Create menu option for accessing the contact list and link to contact list page | 1 | Medium
UI | Create menu option for managing groups and link to group management page | 1 | Medium
UI | Create menu option for accessing payment statistics and history and link to history page | 1 | Low
UI | Create menu option for accessing system settings and link to setting page | 1 | Low
UI | Create menu option for accessing notifications and link to notifications page | 1 | Low
UI | Create transaction creation page 1 (information collection page) | 4 | High
UI | Create transaction creation page 2 (contact selection page) | 4 | High
UI | Create transaction creation page 3 (lenders share page) | 4 | High
UI | Create transaction creation page 4 (division of payments page) | 4 | High
UI | Create transaction resolution page | 4 | High
UI | Create contact list page | 4 | High
UI | Create group management page | 4 | High
UI | Create payment statistics page | 8 | High
UI | Create system setting page | 4 | High
UI | Create notifications page | 4 | High
UI | Display number of notifications on main menu page | 4 | Medium
UI | Populate settings page with account and system options | 4 | High
UI | Create a graphical representation of payment statistics | 8 | Low
UI | Implement a logout button option from main menu | 1 | Low
UI | Create a sound alert upon receiving a notification | 2 | Low
Features | Create method of adding a new contact via email address | 4 | Medium
Features | Add option to delete existing contacts within the contact list page | 2 | Low
Features | Add option to "create new group" within group management page | 2 | Medium
Features | Create display of user's created groups in group management page | 4 | Medium
Features | Add option to change existing group information within group management page | 2 | Low
Features | Provide the ability for a user to save log in information | 4 | Low
Features | Integrate the Facebook API to allow facebook log in into the application | 4 | Low
Features | Allow transaction cost to be split unevenly among contacts when creating a transaction | 2 | Medium
Features | Display group labels and individual contacts on the contact select (creating transactions) | 2 | High
Features | Allow the option of a lender to resolve their created transaction on the resolve page | 4 | Medium
Features | Allow the option of a lender to modify their created transaction on the summary page | 4 | Medium
Features | Set up notifications for contacts of transactions they did not create to confirm them | 8 | Low
Features | Allow the user of the app to send an error report to the developers. | 4 | Low
Features | Allow the borrower to pay off their debt using payments | 4 | Low
Features | Provide a tip calculator sub function in the application | 4 | Medium
Features | Provide the option of imputing the transaction cost in different currencies | 4 | Low
Features | Allow the user to send messages to their contacts through their contact list page | 4 | Medium
Features | Allow the user to track their payment history and income/outgoing money in summary | 4 | High
Features | Allow the transaction creator to place a deadline on repayment of the transaction | 4 | Low
Features | Allow the user to access their transaction history from alternate devices | 8 | Medium
Backend | Create security questions to ask users | 4 | Medium
Backend | Research possible options of where to host database | 4 | High
Backend | Set up database on server | 8 | High
Backend | Create table in database for accounts | 4 | High
Backend | Create table in database for admin | 4 | High
Backend | Create relation in database for transactions | 4 | High
Backend | Create relation in database for groups | 4 | High
Backend | Create realtion in database for friendOf | 4 | High
Backend | Create relation in database for notifications | 4 | Medium
Backend | Write code to query tables | 4 | High
Backend | Write code to update tables | 4 | High
Backend | Create authentication system for user account validation | 8 | High
Backend | Allow importing contacts from google contact list | 8 | Low
Backend | Allow importing contacts from Facebook contact list | 8 | Low
Backend | Create the option for users to change their name | 4 | Low
Backend | Create the option for users to change their email | 4 | Low
Backend | Have transactions and account info saved in the cloud | 8 | Low
248
Note on A1: The Product Backlog is a project-level to do list, and a super-set of all Sprint Backlogs.

## Sprint 1
Sprint 1 Backlog | [5 empty] | Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Backlog Item | Hrs. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Create project files/folders and upload to github | 2 | High | Viquoc | Completed |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a login splash screen | 4 | High | Viquoc | In Progress |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create login credentials input boxes on splash screen | 4 | High | Viquoc | In Progress |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Main Menu page w/ buttons for navigating to other pages | 4 | High | Arnav, Will | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create menu option for creating a transaction and link to transaction creation page | 1 | Medium | Arnav, Will | In Progress |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Create transaction creation page 1 (information collection page) | 4 | High | Huy | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create transaction creation page 2 (contact selection page) | 4 | High | Huy | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create transaction creation page 3 (lenders share page) | 4 | High | Arnav, Will | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create transaction creation page 4 (division of payments page) | 4 | High | Arnav, Will | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create transaction creation page 5 (Summary page) | 4 | Medium | Arnav, Will | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create method of adding a new contact via email address | 4 | Medium | Viquoc | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Research possible options of where to host database | 4 | High | Chase | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Set up database on server | 8 | High | Ryan, Hohyun | In Progress |  |  | 8 | 8 | 8 | 4 | 2 | 2 | 2 | 2 | 2
Create table in database for accounts | 4 | Medium | Ryan, Hohyun | In Progress |  |  | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Create relation in database for transactions | 4 | Medium | Ryan, Hohyun | In Progress |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
Write code to query tables | 4 | Low | Ryan, Hohyun | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Write code to update tables | 4 | Low | Ryan, Hohyun | In Progress |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Ramp up on Android SDK development | 8 | High | All | In Progress |  |  | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Pre Scrum presentation | 2 | High | Tim | Completed |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 1 reporting presentation | 2 | High | Tim | In Progress |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Create GitHub Repository | 1 | High | Tim | Completed |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total Hrs: |  | 80
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 79 | 76 | 61 | 55 | 49 | 49 | 49 | 49 | 49
Ideal | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0